## ENG
Sr. | Section | Station | Block Section | Requested Block Time |  |  | Permitted Block Time |  |  | Availed Block Time |  |  | Burst (mins.) | Remarks | % Perm to Req
|  |  |  | From | To | Duration (HH:mm) | From | To | Duration (HH:mm) | From | To | Duration (HH:mm)
1.1ENGG-CONST.
1 | AJJ-KPD | CTRE |  | 23 Apr 12:25 | 23 Apr 14:25 | 02:00 | 23 Apr 12:25 | 23 Apr 14:25 | 02:00 | 23 Apr 12:25 | 23 Apr 14:40 | 02:15 | 15 | MFI PACKING WORK | 100
2 | MS-TBM | TBM |  | 23 Apr 00:35 | 23 Apr 04:00 | 03:25 | 23 Apr 00:35 | 23 Apr 04:00 | 03:25 | 23 Apr 00:35 | 23 Apr 04:00 | 03:25 |  | ESCALATOR ERECTION WORK | 100
1.2ENGG-OPENLINE
1 | AJJ-KPD |  | CTRE-MDVE | 23 Apr 01:00 | 23 Apr 04:30 | 03:30 | 23 Apr 01:00 | 23 Apr 04:30 | 03:30 | 23 Apr 01:00 | 23 Apr 04:00 | 03:00 | -30 | GRIDER SHIFTING @LUS LC-36. | 100
2 | AJJ-KPD |  | TUG-WJR | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 |  | WW | 100
3 | AJJ-KPD | WJR |  | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 | 23 Apr 01:25 | 23 Apr 04:30 | 03:05 |  | JCB WORK. | 100
4 | AJJ-KPD | KPD |  | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:15 | 02:15 | 15 | ENGG-MAINTENANCE WELDING | 100
5 | AJJ-KPD | CTRE |  | 23 Apr 12:25 | 23 Apr 14:25 | 02:00 | 23 Apr 12:25 | 23 Apr 14:25 | 02:00 | 23 Apr 12:25 | 23 Apr 14:35 | 02:10 | 10 | MFI PACKING WORK | 100
6 | AJJ-KPD | MDVE |  | 23 Apr 22:10 | 24 Apr 00:10 | 02:00 | 23 Apr 22:10 | 24 Apr 00:10 | 02:00 | 23 Apr 22:10 | 24 Apr 00:25 | 02:15 | 15 | MFI57110 PACKING PT51B | 100
7 | AJJ-RU | POI |  | 23 Apr 00:00 | 23 Apr 03:00 | 03:00 | 23 Apr 00:00 | 23 Apr 03:00 | 03:00 | 23 Apr 00:00 | 23 Apr 03:15 | 03:15 | 15 | SEJ RENEWAL WORK | 100
8 | AJJ-RU | AJJN |  | 23 Apr 00:30 | 23 Apr 03:30 | 03:00 | 23 Apr 00:30 | 23 Apr 03:30 | 03:00 | 23 Apr 00:30 | 23 Apr 03:46 | 03:16 | 16 | SWITCH RAIL RENEAL WORK | 100
9 | AJJ-RU | NG |  | 23 Apr 11:45 | 23 Apr 13:45 | 02:00 | 23 Apr 11:45 | 23 Apr 13:45 | 02:00 | 23 Apr 11:45 | 23 Apr 13:52 | 02:07 | 7 | WW BY MFBW PLANT | 100
10 | BBQ-TNPM |  | BBQ-KOK | 23 Apr 00:00 | 23 Apr 01:30 | 01:30 | 23 Apr 00:00 | 23 Apr 01:30 | 01:30 | 23 Apr 00:00 | 23 Apr 02:00 | 02:00 | 30 | RAIL RAIL CLEANING AND PAINTING | 100
11 | BBQ-TRL |  | PEW-VPY | 23 Apr 00:50 | 23 Apr 03:20 | 02:30 | 23 Apr 00:50 | 23 Apr 03:20 | 02:30 | 23 Apr 00:50 | 23 Apr 03:20 | 02:30 |  | MFBW | 100
12 | BBQ-TRL |  | TI-TRL | 23 Apr 01:05 | 23 Apr 03:05 | 02:00 | 23 Apr 01:05 | 23 Apr 03:05 | 02:00 | 23 Apr 01:05 | 23 Apr 03:25 | 02:20 | 20 | ENGG-WELDING OF RAIL JOINTS | 100
13 | BBQ-TRL | PAB |  | 23 Apr 00:08 | 23 Apr 02:08 | 02:00 | 23 Apr 00:08 | 23 Apr 02:08 | 02:00 | 23 Apr 00:08 | 23 Apr 03:08 | 03:00 | 60 | SBCM PACKING | 100
14 | BBQ-TRL | AVD |  | 23 Apr 01:10 | 23 Apr 03:10 | 02:00 | 23 Apr 01:10 | 23 Apr 03:10 | 02:00 | 23 Apr 01:10 | 23 Apr 02:50 | 01:40 | -20 | ENGG-WELDING OF RAIL JOINTS | 100
15 | BBQ-TRL | PAB |  | 23 Apr 23:50 | 24 Apr 01:50 | 02:00 | 23 Apr 23:50 | 24 Apr 01:50 | 02:00 | 23 Apr 23:50 | 24 Apr 02:05 | 02:15 | 15 | SEJ GAP ADJUSTMENT & WW | 100
16 | CGL-AJJ | CJ |  | 23 Apr 00:15 | 23 Apr 04:00 | 03:45 | 23 Apr 00:15 | 23 Apr 04:00 | 03:45 | 23 Apr 00:15 | 23 Apr 04:03 | 03:48 | 3 |  | 100
17 | CGL-AJJ | CJ |  | 23 Apr 23:25 | 24 Apr 01:25 | 02:00 | 23 Apr 23:25 | 24 Apr 01:25 | 02:00 | 23 Apr 23:25 | 24 Apr 02:00 | 02:35 | 35 | PCTM 11043 | 100
18 | CGL-VM |  | MMK-MLMR | 23 Apr 02:30 | 23 Apr 04:30 | 02:00 | 23 Apr 02:30 | 23 Apr 04:30 | 02:00 | 23 Apr 02:30 | 23 Apr 04:30 | 02:00 |  |  | 100
19 | CGL-VM | OV |  | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:30 | 02:30 | 30 |  | 100
20 | CGL-VM | TMV |  | 23 Apr 02:25 | 23 Apr 05:00 | 02:35 | 23 Apr 02:25 | 23 Apr 05:00 | 02:35 | 23 Apr 02:25 | 23 Apr 05:57 | 03:32 | 57 |  | 100
21 | CGL-VM | TZD |  | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 03:50 | 01:05 | -30 |  | 100
22 | KPD-JTJ | GYM |  | 23 Apr 20:55 | 23 Apr 22:55 | 02:00 | 23 Apr 20:55 | 23 Apr 22:55 | 02:00 | 23 Apr 20:55 | 23 Apr 22:55 | 02:00 |  | GJR+W/W | 100
23 | MS-TBM |  | PV-TBM | 23 Apr 14:45 | 23 Apr 15:30 | 00:45 | 23 Apr 14:45 | 23 Apr 15:30 | 00:45 | 23 Apr 14:45 | 23 Apr 16:00 | 01:15 | 30 | BALLAST UNLOADING | 100
24 | MS-TBM | MKK |  | 23 Apr 00:35 | 23 Apr 02:35 | 02:00 | 23 Apr 00:35 | 23 Apr 02:35 | 02:00 | 23 Apr 00:35 | 23 Apr 02:40 | 02:05 | 5 |  | 100
25 | MSB-STM |  | MTMY-MCPK | 23 Apr 23:30 | 24 Apr 04:00 | 04:30 | 23 Apr 23:30 | 24 Apr 04:00 | 04:30 | 23 Apr 23:30 | 24 Apr 03:45 | 04:15 | -15 | RR & WW | 100
26 | MSB-STM | MSB |  | 23 Apr 22:00 | 24 Apr 04:00 | 06:00 | 23 Apr 22:00 | 24 Apr 04:00 | 06:00 | 23 Apr 22:00 | 24 Apr 04:15 | 06:15 | 15 | TRR &FB WW BY MFBW PLANT | 100
27 | TNPM-GDR |  | NYP-DVR | 23 Apr 08:35 | 23 Apr 10:35 | 02:00 | 23 Apr 08:35 | 23 Apr 10:35 | 02:00 | 23 Apr 08:35 | 23 Apr 10:35 | 02:00 |  | DESTRESSING WORK | 100
28 | TNPM-GDR |  | SPE-TADA | 23 Apr 15:30 | 23 Apr 17:30 | 02:00 | 23 Apr 15:30 | 23 Apr 17:30 | 02:00 | 23 Apr 15:30 | 23 Apr 17:30 | 02:00 |  | DESTRESSING AND WELDING WORK | 100
29 | TNPM-GDR | ENR |  | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 03:25 | 03:00 | 60 | RAIL TREK OUT BY JCB | 100
30 | TNPM-GDR | AIP |  | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:00 | 02:00 | 23 Apr 02:00 | 23 Apr 04:45 | 02:45 | 45 | ENGG-RENEWAL SLEEPER REPLACEMENT | 100
31 | TNPM-GDR | PYA |  | 23 Apr 09:10 | 23 Apr 10:10 | 01:00 | 23 Apr 09:10 | 23 Apr 10:10 | 01:00 | 23 Apr 09:10 | 23 Apr 10:10 | 01:00 |  | RAIL TRUCKING OUTR BY DIP LORRY | 100
32 | TNPM-GDR | MJR |  | 23 Apr 23:15 | 24 Apr 01:15 | 02:00 | 23 Apr 23:15 | 24 Apr 01:15 | 02:00 | 23 Apr 23:15 | 24 Apr 01:00 | 01:45 | -15 | UNIMATE MACHINE PACKING WORK | 100
33 | TRL-AJJ |  | KBT-TO | 23 Apr 00:55 | 23 Apr 04:00 | 03:05 | 23 Apr 00:55 | 23 Apr 04:00 | 03:05 | 23 Apr 00:55 | 23 Apr 04:00 | 03:05 |  | ENGG-MAINTENANCE WELDING | 100
1.5TRACMACHINE
1 | CGL-VM |  | OV-CGL | 23 Apr 23:10 | 24 Apr 01:10 | 02:00 | 23 Apr 23:10 | 24 Apr 01:10 | 02:00 | 23 Apr 23:10 | 24 Apr 01:10 | 02:00 |  | BALLEST REGULATING WORK | 100
2 | TNPM-GDR |  | ENR-TVT | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 01:50 | 01:25 | -35 | CSM WORK | 100
3 | TNPM-GDR |  | ENR-TVT | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 02:25 | 02:00 | 23 Apr 00:25 | 23 Apr 03:30 | 03:05 | 65 | CSM | 100
4 | TRL-AJJ |  | KBT-TO | 23 Apr 01:00 | 23 Apr 04:00 | 03:00 | 23 Apr 01:00 | 23 Apr 04:00 | 03:00 | 23 Apr 01:00 | 23 Apr 04:00 | 03:00 |  | DTE PACKING WORK | 100
5 | AJJ-RU |  | VGA-PUT | 23 Apr 00:35 | 23 Apr 03:35 | 03:00 | 23 Apr 00:35 | 23 Apr 03:35 | 03:00 | 23 Apr 00:35 | 23 Apr 03:40 | 03:05 | 5 | DUOMATIC M WORK | 100
6 | CGL-VM | MLMR |  | 23 Apr 23:20 | 24 Apr 01:20 | 02:00 | 23 Apr 23:20 | 24 Apr 01:20 | 02:00 | 23 Apr 23:20 | 24 Apr 00:56 | 01:36 | -24 | PACKING WORK | 100
7 | BBQ-TRL | AVD |  | 23 Apr 01:15 | 23 Apr 03:15 | 02:00 | 23 Apr 01:15 | 23 Apr 03:15 | 02:00 | 23 Apr 01:15 | 23 Apr 03:16 | 02:01 | 1 | PTS 124AB N/R&125AB CBML NOTES | 100
8 | TNPM-GDR | MJR |  | 23 Apr 01:40 | 23 Apr 03:40 | 02:00 | 23 Apr 01:40 | 23 Apr 03:40 | 02:00 | 23 Apr 01:40 | 23 Apr 03:40 | 02:00 |  | UNIMAT 8403 WORK | 100
9 | AJJ-RU | POI |  | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 03:45 | 02:10 | 10 | UTV M WORK | 100
10 | AJJ-RU | TRT |  | 23 Apr 23:40 | 24 Apr 01:10 | 01:30 | 23 Apr 23:40 | 24 Apr 01:10 | 01:30 | 23 Apr 23:40 | 24 Apr 01:10 | 01:30 |  | UNLOADING | 100
11 | BBQ-TRL |  | VPY-BBQ | 23 Apr 00:00 | 23 Apr 00:45 | 00:45 | 23 Apr 00:00 | 23 Apr 00:45 | 00:45 | 23 Apr 00:00 | 23 Apr 00:45 | 00:45 |  | L | 100
12 | MMCC-BBQ |  | BBQ-MAS | 23 Apr 01:00 | 23 Apr 02:00 | 01:00 | 23 Apr 01:00 | 23 Apr 02:00 | 01:00 | 23 Apr 01:00 | 23 Apr 02:55 | 01:55 | 55 | L | 100

## SIGNAL
Sr. | Section | Station | Block Section | Requested Block Time |  |  | Permitted Block Time |  |  | Availed Block Time |  |  | Burst (mins.) | Remarks | % Perm to Req
|  |  |  | From | To | Duration (HH:mm) | From | To | Duration (HH:mm) | From | To | Duration (HH:mm)
1.3SIGNAL
1 | BBQ-TRL | ABU |  | 23 Apr 01:20 | 23 Apr 02:05 | 00:45 | 23 Apr 01:20 | 23 Apr 02:05 | 00:45 | 23 Apr 01:20 | 23 Apr 02:05 | 00:45 |  | EI# AMC | 100
2 | KPD-JTJ |  | AB-VGM | 23 Apr 14:45 | 23 Apr 15:30 | 00:45 | 23 Apr 14:45 | 23 Apr 15:30 | 00:45 | 23 Apr 14:45 | 23 Apr 15:44 | 00:59 | 14 | ELD CHECKING | 100
3 | KPD-JTJ | KDY |  | 23 Apr 15:20 | 23 Apr 16:05 | 00:45 | 23 Apr 15:20 | 23 Apr 16:05 | 00:45 | 23 Apr 15:20 | 23 Apr 16:05 | 00:45 |  | RECONNECTION/DISCONNECTION | 100
4 | MSB-STM | MSB |  | 23 Apr 00:10 | 23 Apr 02:10 | 02:00 | 23 Apr 00:10 | 23 Apr 02:10 | 02:00 | 23 Apr 00:10 | 23 Apr 02:35 | 02:25 | 25 | 128 PT RELAY SHIFTING WORK | 100
5 | MSB-TNP | RPM |  | 23 Apr 01:25 | 23 Apr 02:15 | 00:50 | 23 Apr 01:25 | 23 Apr 02:15 | 00:50 | 23 Apr 01:25 | 23 Apr 02:15 | 00:50 |  | RELAY PARELLELLING WORKS | 100
6 | TNPM-GDR |  | ENR-TVT | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 |  | EI AMC WORK | 100
7 | TNPM-GDR |  | TVT-ENR | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 |  | EI AMC WORK | 100
8 | TNPM-GDR | ODUR |  | 23 Apr 12:30 | 23 Apr 14:00 | 01:30 | 23 Apr 12:30 | 23 Apr 14:00 | 01:30 | 23 Apr 12:30 | 23 Apr 14:05 | 01:35 | 5 | CABLE MEGGARING WORK | 100
9 | TNPM-GDR | AKM |  | 23 Apr 13:05 | 23 Apr 13:25 | 00:20 | 23 Apr 13:05 | 23 Apr 13:25 | 00:20 | 23 Apr 13:05 | 23 Apr 13:30 | 00:25 | 5 | EI AMC WORK | 100
10 | TRL-AJJ | KBT |  | 23 Apr 00:45 | 23 Apr 01:45 | 01:00 | 23 Apr 00:45 | 23 Apr 01:45 | 01:00 | 23 Apr 00:45 | 23 Apr 01:45 | 01:00 |  | ALL LINES | 100

## TRD
Sr. | Section | Station | Block Section | Requested Block Time |  |  | Permitted Block Time |  |  | Availed Block Time |  |  | Burst (mins.) | Remarks | % Perm to Req
|  |  |  | From | To | Duration (HH:mm) | From | To | Duration (HH:mm) | From | To | Duration (HH:mm)
1.4TRACK DISTR.
1 | AJJ-KPD |  | CTRE-MDVE | 23 Apr 01:00 | 23 Apr 04:30 | 03:30 | 23 Apr 01:00 | 23 Apr 04:30 | 03:30 | 23 Apr 01:00 | 23 Apr 04:00 | 03:00 | -30 | PTW | 100
2 | AJJ-KPD |  | MLPM-AJJ | 23 Apr 23:17 | 24 Apr 00:20 | 01:03 | 23 Apr 23:17 | 24 Apr 00:20 | 01:03 | 23 Apr 23:17 | 24 Apr 00:28 | 01:11 | 8 | 71KM TW WORKIBNG | 100
3 | AJJ-RU |  | NG-POI | 23 Apr 01:20 | 23 Apr 02:20 | 01:00 | 23 Apr 01:20 | 23 Apr 02:20 | 01:00 | 23 Apr 01:20 | 23 Apr 02:49 | 01:29 | 29 | TRTN-OHE-LADDER TROLLEY WORKING | 100
4 | AJJ-RU |  | NG-VGA | 23 Apr 01:50 | 23 Apr 02:50 | 01:00 | 23 Apr 01:50 | 23 Apr 02:50 | 01:00 | 23 Apr 01:50 | 23 Apr 03:40 | 01:50 | 50 | DSL+BFR WORK | 100
5 | AJJ-RU |  | POI-TRT | 23 Apr 01:20 | 23 Apr 02:20 | 01:00 | 23 Apr 01:20 | 23 Apr 02:20 | 01:00 | 23 Apr 01:20 | 23 Apr 02:49 | 01:29 | 29 | TRTN-OHE-LADDER TROLLEY WORKING | 100
6 | BBQ-TNPM |  | BBQ-KOK | 23 Apr 00:05 | 23 Apr 01:30 | 01:25 | 23 Apr 00:05 | 23 Apr 01:30 | 01:25 | 23 Apr 00:05 | 23 Apr 02:05 | 02:00 | 35 | TRTN-OHE-LADDER TROLLEY WORKING | 100
7 | BBQ-TRL |  | AVD-PAB | 23 Apr 02:05 | 23 Apr 02:50 | 00:45 | 23 Apr 02:05 | 23 Apr 02:50 | 00:45 | 23 Apr 02:05 | 23 Apr 02:51 | 00:46 | 1 | TRTN-OHE-LADDER TROLLEY WORKING | 100
8 | BBQ-TRL |  | PAB-AVD | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100
9 | BBQ-TRL |  | PAB-TI | 23 Apr 02:05 | 23 Apr 02:50 | 00:45 | 23 Apr 02:05 | 23 Apr 02:50 | 00:45 | 23 Apr 02:05 | 23 Apr 02:51 | 00:46 | 1 | TRTN-OHE-LADDER TROLLEY WORKING | 100
10 | BBQ-TRL |  | TI-PAB | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 | 23 Apr 00:35 | 23 Apr 01:20 | 00:45 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100
11 | BBQ-TRL |  | VPY-VLK | 23 Apr 01:20 | 23 Apr 02:05 | 00:45 | 23 Apr 01:20 | 23 Apr 02:05 | 00:45 | 23 Apr 01:20 | 23 Apr 02:35 | 01:15 | 30 | TRTN-OHE-TOWER WAGON WORKING | 100
12 | CGL-VM |  | MLMR-TZD | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 03:50 | 01:05 | -30 |  | 100
13 | CGL-VM |  | TZD-OLA | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 04:20 | 01:35 | 23 Apr 02:45 | 23 Apr 03:50 | 01:05 | -30 |  | 100
14 | KPD-JTJ |  | LTI-KPD | 23 Apr 21:25 | 23 Apr 23:25 | 02:00 | 23 Apr 21:25 | 23 Apr 23:25 | 02:00 | 23 Apr 21:25 | 23 Apr 23:30 | 02:05 | 5 | TRTN-OHE-LADDER TROLLEY WORKING | 100
15 | KPD-JTJ |  | VGM-VN | 23 Apr 15:15 | 23 Apr 16:00 | 00:45 | 23 Apr 15:15 | 23 Apr 16:00 | 00:45 | 23 Apr 15:15 | 23 Apr 16:01 | 00:46 | 1 | TRTN-OHE-LADDER TROLLEY WORKING | 100
16 | KPD-JTJ |  | VN-KDY | 23 Apr 15:15 | 23 Apr 16:00 | 00:45 | 23 Apr 15:15 | 23 Apr 16:00 | 00:45 | 23 Apr 15:15 | 23 Apr 16:01 | 00:46 | 1 | TRTN-OHE-LADDER TROLLEY WORKING | 100
17 | KPD-JTJ | VN |  | 23 Apr 21:05 | 23 Apr 22:35 | 01:30 | 23 Apr 21:05 | 23 Apr 22:35 | 01:30 | 23 Apr 21:05 | 23 Apr 21:35 | 00:30 | -60 | TRTN-OHE-TOWER WAGON WORKING | 100
18 | KPD-JTJ | VN |  | 23 Apr 21:05 | 23 Apr 22:35 | 01:30 | 23 Apr 21:05 | 23 Apr 22:35 | 01:30 | 23 Apr 21:05 | 23 Apr 22:45 | 01:40 | 10 | TRTN-OHE-TOWER WAGON WORKING | 100
19 | MS-TBM |  | MKK-MS | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 02:19 | 01:29 | 29 |  | 100
20 | MS-TBM |  | MKK-STM | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 |  | PB DN SUB LT WORK AT 15 KM | 100
21 | MS-TBM |  | MS-MKK | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 |  | PB DN SUB LT WORK AT 15 KM | 100
22 | MS-TBM |  | PV-STM | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:56 | 01:06 | 6 |  | 100
23 | MS-TBM |  | STM-MKK | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:50 | 01:00 | 23 Apr 00:50 | 23 Apr 01:56 | 01:06 | 6 |  | 100
24 | MS-TBM |  | STM-PV | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 | 23 Apr 01:45 | 23 Apr 03:30 | 01:45 |  | PB DN SUB LT WORK AT 15 KM | 100
25 | MS-TBM | MKK |  | 23 Apr 00:35 | 23 Apr 02:35 | 02:00 | 23 Apr 00:35 | 23 Apr 02:35 | 02:00 | 23 Apr 00:35 | 23 Apr 01:53 | 01:18 | -42 |  | 100
26 | MSB-MS |  | MSB-MS | 23 Apr 00:35 | 23 Apr 01:45 | 01:10 | 23 Apr 00:35 | 23 Apr 01:45 | 01:10 | 23 Apr 00:35 | 23 Apr 02:19 | 01:44 | 34 |  | 100
27 | MSB-TNP |  | VPY-WST | 23 Apr 00:50 | 23 Apr 01:35 | 00:45 | 23 Apr 00:50 | 23 Apr 01:35 | 00:45 | 23 Apr 00:50 | 23 Apr 02:19 | 01:29 | 44 | TRTN-OHE-LADDER TROLLEY WORKING | 100
28 | TNPM-GDR |  | DVR-NYP | 23 Apr 01:10 | 23 Apr 02:40 | 01:30 | 23 Apr 01:10 | 23 Apr 02:40 | 01:30 | 23 Apr 01:10 | 23 Apr 04:10 | 03:00 | 90 | TRTN-OHE-LADDER TROLLEY WORKING | 100
29 | TNPM-GDR |  | ENR-TVT | 23 Apr 02:25 | 23 Apr 02:55 | 00:30 | 23 Apr 02:25 | 23 Apr 02:55 | 00:30 | 23 Apr 02:25 | 23 Apr 03:00 | 00:35 | 5 | TRTN-OHE-TOWER WAGON WORKING | 100
30 | TNPM-GDR |  | NYP-PYA | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 04:01 | 02:26 | 26 | TRTN-OHE-LADDER TROLLEY WORKING | 100
31 | TNPM-GDR |  | NYP-PYA | 23 Apr 13:10 | 23 Apr 14:10 | 01:00 | 23 Apr 13:10 | 23 Apr 14:10 | 01:00 | 23 Apr 13:10 | 23 Apr 14:10 | 01:00 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100
32 | TNPM-GDR |  | PYA-NYP | 23 Apr 13:55 | 23 Apr 14:55 | 01:00 | 23 Apr 13:55 | 23 Apr 14:55 | 01:00 | 23 Apr 13:55 | 23 Apr 15:00 | 01:05 | 5 | TRTN-OHE-TOWER WAGON WORKING | 100
33 | TNPM-GDR |  | PYA-ODUR | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 03:35 | 02:00 | 23 Apr 01:35 | 23 Apr 04:01 | 02:26 | 26 | TRTN-OHE-LADDER TROLLEY WORKING | 100
34 | TNPM-GDR |  | TVT-ENR | 23 Apr 03:10 | 23 Apr 03:50 | 00:40 | 23 Apr 03:10 | 23 Apr 03:50 | 00:40 | 23 Apr 03:10 | 23 Apr 04:00 | 00:50 | 10 | TRTN-OHE-TOWER WAGON WORKING | 100
35 | TRL-AJJ |  | KBT-TRL | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100
36 | TRL-AJJ |  | TO-KBT | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 | 23 Apr 00:00 | 23 Apr 01:40 | 01:40 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100
37 | TRL-AJJ | AJJ |  | 23 Apr 00:50 | 23 Apr 02:10 | 01:20 | 23 Apr 00:50 | 23 Apr 02:10 | 01:20 | 23 Apr 00:50 | 23 Apr 02:10 | 01:20 |  | AJJ NI WORK, | 100
38 | TRL-AJJ | AJJ |  | 23 Apr 13:20 | 23 Apr 14:05 | 00:45 | 23 Apr 13:20 | 23 Apr 14:05 | 00:45 | 23 Apr 13:20 | 23 Apr 14:05 | 00:45 |  | TRTN-OHE-LADDER TROLLEY WORKING | 100